STATE OF WISCONSIN

DEPARTMENT OF VETERANS AFFAIRS

PROJECT DESCRIPTION AND

REQUEST FOR ARCHITECTURAL/ENGINEERING SERVICES

Shemanske Hall Renovations for

USDVA Community Based Outpatient Clinic

Wisconsin Veterans Homes - Union Grove

Union Grove, Wisconsin

Project # 13A2M

June 2013

TABLE OF CONTENTS

- Request Statement	3

- Project Scope	3

A.  Project Description

B.  Project Location

C.  Project Background and Existing Conditions

- Project Requirements and Design Considerations	3

- Proposed Timetable	3

- Proposed Budget	4

- Agency Contact	4

- AE Scope of Services	4

  - Request Statement

The Wisconsin Department of Veterans Affairs is requesting the selection of an Architect/Engineer to provide full design services including design and construction administration for the renovation of Shemanske Hall to meet the needs of the USDVA Community Based Outpatient Clinic (CBOC) on the grounds of the Veterans Home - Union Grove (Home) per the Program Statement.

- Project Scope

A.  Project Description

The project will renovate approximately 11,500 GSF of 26,964 GSF in Shemanske Hall for use as a CBOC by the federal VA.  Renovations will include demolition and construction within the 11,500 GSF identified for the clinic. The clinic will have spaces for admissions, patient exams, public toilets, offices, conference room, break/locker room, storage, and video communications with physicians at regional clinics and hospitals.

B.  Project Location

Union Grove, Wisconsin

Wisconsin Veterans Home

C.  Project Background and Existing Conditions

Currently the CBOC is located in Wallace Hall on the Southern Wisconsin Center Campus for the Developmentally Disabled. The number and size of the programs provided by the CBOC are increasing so there is a need for additional space. Wallace Hall is not able to accommodate the program expansion. Shemanske Hall was chosen as the best site for the new CBOC at Union Grove.

  - Project Requirements and Design Considerations

Shemanske Hall is approximately 26,964 GSF. Of that approximately 11,500GSF will be renovated.  Renovation will include the demolition of walls, plumbing and electrical fixtures, wiring and piping, flooring and ceilings. Construction will consist of new walls, lavatories, ADA bathrooms, data and telephone lines, security, lighting, ceilings and flooring.

  - Proposed Timetable

| A/E Advertisement | June, 2013 |
| --- | --- |
| A/E Selection | July, 2013 |
| Design Report to Building Commission | December, 2013 |
| Bid Opening | April, 2014 |
| Construction Begins | May, 2014 |
| Substantial Completion | October, 2014 |

- Proposed Budget

| Construction | $ |
| --- | --- |
| Contingency |  |
| Architect/Engineer |  |
| DSF Fees |  |
| Total Project Budget | $2,473,900 |

- Agency Contact: Susan Mattix, 608-264-6093  susan.mattix@dva.wisconsin.gov

- AE Scope of Services

The AE will meet the requirements of the DFD AE Policy and Procedure Manual.